## Open - In progress
Epic	Key	Story	Sub-task	Estimate	Status	Date started	Date completed	Comments

Networking	CZ-7	Review resume for updating			Open
			Meet with AB!	1	Open
			Get local copy of personnel folder from work	0.5	Open
			Review SAP Config Eng resume	1	Open
			Review LinkedIn resume	1	Open

Frameworks	CZ-4	Explore Spring framework			In progress
			Work thru serving web content demo	1	In progress	11/22/17

Frameworks	CZ-5	Explore Maven			Open
			Work thru serving web content demo	1	In progress	11/22/17

Demo	CZ-6	Design Project			Open
			UI		Open			js single-page framework
			API		Open			REST
			Service layer		Open			Java
			DataSource		Open			Existing API – json?
			DataSource		Open			Persist json from above to DB, use JPA

Networking	CZ-8	Style resume			Open

Networking	CZ-9	Update LinkedIn			Open
			Add headshot		Open
			Update profile		Open

Networking	CZ-11	Create StackOverflow profile			Open

Networking	CZ-10	Check out remote.com			Open

Frameworks	CZ-12	Explore DevOps			Open
			Build		Open			Jenkins/AWS?
			Test		Open			Jenkins/AWS?
			Deploy		Open			Jenkins/AWS?

Management	CZ-13	Update task tracking				11/18/17		Looked at PivotTracker. Others include Trello...
			Explore more sophisticated tools	2	In progress	11/18/17		Timebox this!

## Complete
Infrastructure	CZ-3	Set up IDE			Complete
			Install eclipse oxygen	1	Complete	11/22/17	11/22/17
			Configure eclipse oxygen	1	Complete	11/22/17	11/22/17	Configure for git, maven at least
			Install java 1.8 JDK	0.5	Complete	11/22/17	11/22/17

Management	CZ-1	Create task tracking			Complete	11/19/17	11/25/17	Creating the spreadsheet is easy; exploration needs to be timeboxed (moved to CZ-13)
			Start spreadsheet	0.5	Complete	11/19/17	11/19/17
			Add s/s to git	0.5	Complete	11/19/17	11/19/17

Infrastructure	CZ-2	Create repository			Complete	11/19/17	11/25/17
			Init local repo	0.5	Complete	11/19/17	11/19/17
			Push to github	0.5	Complete	11/19/17	11/19/17
			Configure repo security	0.5	Complete	11/25/17	11/25/17	Created an organization, added heaslj with admin rights on organization's repositories; created career-3.1 team to work on challenge-zone repo and added heaslj to that team